## Sheet1
2025/2026 KIGALI CITY Annual Procurement Plan
S/N | Type | Title of tender | Source of Funds | Tendering method | Planned tender document preparation date | Planned Publication date | Planned Bid opening date | Planned Provisional Notification date | Planned Contract signing date | Recruitment of the supervising firm (Y/N) | Planned Contract Management start date | Planned Contract closure date | Other information
1 | Goods | Supply of circular concrete poles and metallic steel poles for street lights maintenance in the City of Kigali | Government Of Rwanda | National Competitive Bidding | 22/08/2025 | 26/08/2025 | 18/09/2025 | 08/10/2025 | 08/11/2025 | N | 08/11/2025 | 07/11/2026
2 |  | Supply of sand for construction of retaining walls in schools on framework contract (1 Lot by District) | Government Of Rwanda | National Competitive Bidding | 22/08/2025 | 26/08/2025 | 18/09/2025 | 08/10/2025 | 08/11/2025 | N | 08/11/2025 | 07/11/2026
3 |  | Supply of hardcore stones for construction of retaining walls in schools on framework contract-(1 Lot by District) | Government Of Rwanda | National Competitive Bidding | 24/08/2025 | 26/08/2025 | 19/09/2025 | 08/10/2025 | 08/11/2025 | N | 08/11/2025 | 07/11/2026
4 |  | Supply of hardware materials and gravel for construction of retaining walls in schools on framework contract(1 Lot by District) | Government Of Rwanda | National Competitive Bidding | 22/08/2025 | 26/08/2025 | 18/09/2025 | 08/10/2025 | 08/11/2025 | N | 08/11/2025 | 07/11/2026
5 |  | A supply of construction materials, which includes the installation of electrical equipment and water tanks in schools. Framework contract (1 Lot by District) | Government Of Rwanda | National Competitive Bidding | 24/08/2025 | 28/08/2025 | 22/09/2025 | 17/10/2025 | 17/11/2025 | N | 17/11/2025 | 16/11/2026
6 | Goods | Purchase of New CoK operational vehicle | Government Of Rwanda | National Competitive Bidding | 25/08/2025 | 29/08/2025 | 22/09/2025 | 13/10/2025 | 22/10/2025 | N | 22/10/2025 | 22/03/2026 | Timelines my change
7 |  | Operationalization of Home Based ECD(HBECD)/porridge for 251HBECD (Gasab0:187, Kicukiro:19;Nyarugenge:45) | Government Of Rwanda | National Competitive Bidding | 25/08/2025 | 29/08/2025 | 22/09/2025 | 13/10/2025 | 01/11/2025 | N | 01/11/2025 | 01/03/2026 | Timeslines my change
8 |  | Tender for supplying sports equipment &materials | Government Of Rwanda | National Competitive Bidding | 25/08/2025 | 29/08/2025 | 22/09/2025 | 13/10/2025 | 31/10/2025 | N | 31/10/2025 | 31/10/2026 | Timelines my change
9 |  | Supply of IT equipment to the RUDPII Staff | Grants | National Competitive Bidding | 26/08/2025 | 29/08/2025 | 30/09/2025 | 21/10/2025 | 31/10/2025 | N | 31/10/2025 | 31/12/2025 | Timelines may change
10 |  | Tender for supply of pre-cooked beans | Government Of Rwanda | National Competitive Bidding | 22/08/2025 | 30/08/2025 | 22/09/2025 | 15/10/2025 | 07/11/2025 | N | 07/11/2025 | 07/11/2026 | Timelines my change
11 |  | Tender for Purchase trucks for road cleaning and greening/Watering services. | Government Of Rwanda | National Competitive Bidding | 25/08/2025 | 30/08/2025 | 22/09/2025 | 12/10/2025 | 12/11/2025 | N | 12/11/2025 | 12/03/2026
12 |  | Acquisition of new communication equipment | Government Of Rwanda | National Competitive Bidding | 13/09/2025 | 20/09/2025 | 14/10/2025 | 30/10/2025 | 30/11/2025 | N | 30/11/2025 | 30/03/2026
13 |  | Girinka Minimum packages | Government Of Rwanda | National Competitive Bidding | 23/09/2025 | 30/09/2025 | 21/10/2025 | 30/10/2025 | 10/11/2025 | N | 10/11/2025 | 30/06/2026 | Timelines my change
14 | Goods | Supply of Desktop Computer and GIS Data Collector Tablet | Government Of Rwanda | National Competitive Bidding | 23/09/2025 | 30/09/2025 | 22/10/2025 | 12/11/2025 | 12/12/2025 | N | 12/12/2025 | 12/04/2026
15 |  | Purchase lime to the Farmers | Government Of Rwanda | National Competitive Bidding | 23/09/2025 | 30/09/2025 | 21/10/2025 | 30/10/2025 | 10/11/2025 | N | 10/11/2025 | 30/06/2026 | TimeLines my change
16 |  | Purchase Cows for Girinka Program beneficiairies | Government Of Rwanda | National Competitive Bidding | 23/09/2025 | 30/09/2025 | 21/10/2025 | 30/10/2025 | 10/11/2025 | N | 10/11/2025 | 30/06/2026 | Timelines my change
17 |  | Procure and install furniture and equipment (Chairs, IT tools, Security and safety gargets like walk through metal detector, luggage scanner, etc) | Government Of Rwanda | National Competitive Bidding | 24/10/2025 | 31/10/2025 | 21/11/2025 | 22/12/2025 | 16/01/2026 | N | 16/01/2026 | 22/06/2026 | Timelines my change
18 |  | Supply of two operation vehicles | Grants | National Competitive Bidding | 12/11/2025 | 28/11/2025 | 31/12/2025 | 21/01/2026 | 30/01/2026 | N | 30/01/2026 | 30/06/2026 | Timelines may change due to other factors
19 |  | Tender for the Purchase of office furniture (Desks, chairs,..) for KISUP team | Grants | National Competitive Bidding | 17/11/2025 | 01/12/2025 | 31/12/2025 | 21/01/2026 | 27/02/2026 | N | 27/02/2026 | 29/05/2026
20 |  | Tender for the Purchase of video and audio conference devices for KISUP | Government Of Rwanda | National Competitive Bidding | 17/11/2025 | 01/12/2025 | 01/01/2026 | 22/01/2026 | 16/02/2026 | N | 16/02/2026 | 30/04/2026
21 | Goods | Tender for supply of Battery Electric Buses and chargers | Grants | International Competitive Bidding | 06/04/2026 | 20/04/2026 | 15/06/2026 | 30/06/2026 | 21/07/2026 | N | 21/07/2026 | 30/10/2026 | The timeline can change
22 |  | Supply and maintenance of smart LEDs (Light Emitting Diode) lights, decorative lights and related accessories required for street lights and public spaces maintenance | Government Of Rwanda | National Competitive Bidding | [7 empty] | 04/12/2025
23 |  | Tender for supply of Food stuff and necessities for Kigali transit center | Government Of Rwanda | National Competitive Bidding | [7 empty] | 13/02/2026
24 |  | Supply items for youth to Iwawa | Government Of Rwanda | National Competitive Bidding | [7 empty] | 16/01/2026
25 |  | Supply of circular concrete poles and metallic steel poles for street lights maintenance in the City of Kigali Lot 2 | Government Of Rwanda | National Competitive Bidding | [7 empty] | 19/12/2025
26 |  | School feeding provided to schools | Grants | Single Source | [7 empty] | 23/11/2025
27 |  | Purchase office equipment and furniture | Government Of Rwanda | National Competitive Bidding | [7 empty] | 15/11/2025
28 | Goods | Supply of circular concrete poles and metallic steel poles | Government Of Rwanda | National Competitive Bidding | [7 empty] | 19/12/2025
29 |  | Supply of Fuel | Government Of Rwanda | National Competitive Bidding | [7 empty] | 01/08/2025
30 |  | Supply of Furnitures (Desk ,Table&Chairs) | Government Of Rwanda | National Competitive Bidding | [7 empty] | 10/11/2025
31 |  | Supply of refreshments | Government Of Rwanda | National Competitive Bidding | [7 empty] | 12/03/2026
32 |  | School feeding provided to Schools | Government Of Rwanda | International Competitive Bidding | [7 empty] | 23/11/2025
33 |  | Productive Asset of VUP Multi-sectoral approch | Government Of Rwanda | National Competitive Bidding | [7 empty] | 08/02/2026
34 |  | Provide electricity to CoK Schools | Government Of Rwanda | National Competitive Bidding | [7 empty] | 02/02/2026
35 |  | Supply of Personal Protective equipment (PPE) | Government Of Rwanda | National Competitive Bidding | [7 empty] | 18/08/2025
36 | Goods | Tender for supply and installation and maintenance of Dustbins | Government Of Rwanda | National Competitive Bidding | [7 empty] | 26/02/2026
37 |  | Tender to install, oparate and maintain street lights in selected streets in the City of Kigali through advertisement mechanism Lot 2 | Government Of Rwanda | National Competitive Bidding | [7 empty] | 14/08/2025
38 |  | Supply of office stationaries | Government Of Rwanda | National Competitive Bidding | [7 empty] | 28/01/2026
39 |  | Tender for Medical supply for Kigali transit center | Government Of Rwanda | National Competitive Bidding | [7 empty] | 05/02/2026
40 | Works | Maintenance of new neighborhood roads in collaboration with citizen the City of Kigali | Government Of Rwanda | National Competitive Bidding | 22/08/2025 | 26/08/2025 | 18/09/2025 | 08/10/2025 | 08/11/2025 | Y | 08/11/2025 | 07/11/2026
41 |  | Maintenance of waste water treatment plants | Government Of Rwanda | National Competitive Bidding | 24/08/2025 | 28/08/2025 | 22/09/2025 | 18/10/2025 | 18/11/2025 | N | 18/11/2025 | 17/11/2026
42 |  | Construction of artificial playing ground | Government Of Rwanda | National Competitive Bidding | 25/08/2025 | 29/08/2025 | 22/09/2025 | 13/10/2025 | 23/10/2025 | N | 23/10/2025 | 23/02/2026 | Timelines my change
43 |  | Renovation of Muhima HC Maternity | Government Of Rwanda | National Competitive Bidding | 25/08/2025 | 29/08/2025 | 22/09/2025 | 13/10/2025 | 23/10/2025 | N | 23/10/2025 | 23/02/2026 | Timelines my change
44 | Works | Tender for Framework contract for ravine construction/rehabilitation | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 09/10/2025 | 09/11/2025 | Y | 09/11/2025 | 08/11/2026 | No comment
45 |  | Tender for Framework contract for building construction | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 10/10/2025 | 10/11/2025 | Y | 10/11/2025 | 09/11/2026 | No comment
46 |  | Tender for Framework contract for road construction | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 10/10/2025 | 10/11/2025 | Y | 10/11/2025 | 09/11/2026 | No comment
47 |  | Tender for Framework contract for retaining walls construction | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 10/10/2025 | 10/11/2025 | Y | 10/11/2025 | 09/11/2026 | No comment
48 |  | Tender for Design and Build Contractor for Nyabugogo Multi Modal Transit Terminal and terminal area | Grants | International Competitive Bidding | 09/09/2025 | 23/09/2025 | 14/11/2025 | 28/11/2025 | 15/12/2025 | Y | 15/12/2025 | 11/12/2028 | Timelines can change
49 |  | Construction of Shelter to the needy Genocide Survivors | Government Of Rwanda | Force Account | 01/10/2025 | 15/10/2025 | 31/10/2025 | 14/11/2025 | 01/12/2025 | Y | 01/12/2025 | 01/06/2026 | Timelines my change
50 |  | Hiring the contractor for construction of open spaces (Lot 2) completed | Grants | National Competitive Bidding | 31/12/2025 | 01/01/2026 | 16/02/2026 | 03/03/2026 | 15/04/2026 | Y | 15/04/2026 | 16/04/2027
51 |  | Construction of Nyirabwana Ravine/ Kibagabaga( Design and build) | Government Of Rwanda | National Competitive Bidding | 23/02/2026 | 27/02/2026 | 23/03/2026 | 13/04/2026 | 13/05/2026 | Y | 13/05/2026 | 12/09/2026
52 | Works | Tender for E-buses depots/charging infrastructure construction and installation of chargers | Grants | International Competitive Bidding | 12/01/2026 | 27/02/2026 | 15/04/2026 | 30/04/2026 | 22/05/2026 | Y | 22/05/2026 | 31/12/2026
53 |  | Construction of Busanza Youth Centre /Playground | Government Of Rwanda | National Competitive Bidding | 23/03/2026 | 30/03/2026 | 22/04/2026 | 10/05/2026 | 10/06/2026 | Y | 10/06/2026 | 09/09/2026
54 |  | Tender for maintenance of marrum and cobblestone roads in bad conditions | Government Of Rwanda | National Competitive Bidding | [7 empty] | 12/11/2025
55 |  | Tender for execution of regular desilting works at the most critical flooding spots and maintenance of drainage channels and ravines across the city of Kigali | Government Of Rwanda | National Competitive Bidding | [7 empty] | 29/10/2025
56 |  | Tender for construction works of landscape, small workshop and 1 Block for Rental Housing Scheme in Mpazi | Grants | Single Source | [7 empty] | 07/04/2026
57 |  | Hiring the Contractor for implementing the package 2 of civil work 6 Flood hotspot | Grants | International Competitive Bidding | [7 empty] | 27/11/2025
58 | Works | Construction of Gatenga Informal Settlement upgrading works | Grants | International Competitive Bidding | [7 empty] | 31/10/2025
59 |  | Contractor for construction and Maintenance of Neighborhood roads in partnership with citizens | Government Of Rwanda | National Competitive Bidding | [7 empty] | 29/10/2025
60 |  | Eligible vulnerable households supported with adequate shelter | Government Of Rwanda | Force Account | [7 empty] | 09/10/2025
61 |  | Completion of remaining works of Neighbordhood Road In Nyarugenge and Kicukiro Districts | Government Of Rwanda | Single Source | [7 empty] | 23/11/2025
62 |  | Construction of Nyabisindu &Nyagatovu Informal Settlements upgrading works | Grants | International Competitive Bidding | [7 empty] | 26/09/2025
63 |  | Construction of retaining wall at GS Kariyeri | Government Of Rwanda | National Competitive Bidding | [7 empty] | 01/12/2025
64 |  | Tender to implement Kigali City Infrastructure project | Government Of Rwanda | Single Source | [7 empty] | 04/05/2031
65 | Works | Construction work of Nyabisindu rehousing project in the City of Kigali | Grants | National Competitive Bidding | [7 empty] | 08/12/2025
66 |  | Maintenance IDP Model | Government Of Rwanda | National Competitive Bidding | [7 empty] | 14/02/2026
67 |  | Extension of Mageragere Memorial Genocide Memorial site Phase 2 | Government Of Rwanda | Force Account | [7 empty] | 29/04/2026
68 |  | Hiring the Contractor for implementing the package 1 of civil work 6 Flood hotspot | Grants | International Competitive Bidding | [7 empty] | 06/08/2025
69 | Consultant Services | Hiring a consultant for conducting business data analysis | Government Of Rwanda | National Competitive Bidding | 01/08/2025 | 04/08/2025 | 27/08/2025 | 15/09/2025 | 14/10/2025 | N | 14/10/2025 | 14/02/2026 | Timelines my change
70 |  | Tender for Profiling the City of Kigali, through a coffee table book | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 10/10/2025 | 10/11/2025 | N | 10/11/2025 | 09/03/2026
71 |  | Study for Construction of Busanza Youth Centre /Playground | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 10/10/2025 | 10/11/2025 | N | 10/11/2025 | 09/03/2026
72 |  | Supervision of road maintenance, ravine and de-silting works in the city of Kigali | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 17/10/2025 | 17/11/2025 | N | 17/11/2025 | 16/11/2026
73 | Consultant Services | Tender for supervision for Framework contracts for retaining walls construction/building construction/Road construction/ Ravine construction | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 09/10/2025 | 09/11/2025 | N | 09/11/2025 | 08/11/2026 | No comment
74 |  | Supervision of Shelter to the needy Genocide Survivors | Government Of Rwanda | National Competitive Bidding | 15/09/2025 | 26/09/2025 | 24/10/2025 | 07/11/2025 | 01/12/2025 | N | 01/12/2025 | 01/07/2026 | Timelines my change
75 |  | Preparation of phase II of fleet renewal program, including transaction advisory and a detailed design for E-bus project | Grants | International Competitive Bidding | 01/09/2025 | 30/09/2025 | 31/10/2025 | 21/11/2025 | 08/12/2025 | N | 08/12/2025 | 31/12/2026
76 |  | Individual consultant to provide technical assistance services of Procurement Expert to City of Kigali | Grants | International Competitive Bidding | 26/08/2025 | 30/09/2025 | 30/10/2025 | 21/11/2025 | 29/12/2025 | N | 29/12/2025 | 30/12/2026 | Timelines may change
77 |  | Provide consultancy services to produce detailed study and design of Kigali 3D monument at Mont Kigali and USA Embassy monument | Government Of Rwanda | National Competitive Bidding | 23/09/2025 | 30/09/2025 | 22/10/2025 | 12/11/2025 | 12/12/2025 | N | 12/12/2025 | 11/05/2026
78 | Consultant Services | Consultancy services to conduct a household survey in Mpazi to assess changes in leaving conditions deriving from the rehousing process to inform future projects in Kigali | Grants | National Competitive Bidding | 03/10/2025 | 06/10/2025 | 31/10/2025 | 20/11/2025 | 01/12/2025 | N | 01/12/2025 | 01/05/2026 | Timelines may change
79 |  | Consultancy for feasibility study and design for Transit-Oriented Development of Nyabugogo Multi-Modal Transit Terminal area and Non-motorized Transport of defined low-income neighborhoods | Grants | International Competitive Bidding | 06/10/2025 | 20/10/2025 | 21/11/2025 | 28/11/2025 | 22/12/2025 | N | 22/12/2025 | 22/07/2026
80 |  | Hiring a consultancy firm for conducting traffic simulation for transport network of the City of Kigali | Grants | International Competitive Bidding | 06/10/2025 | 20/10/2025 | 28/11/2025 | 22/12/2025 | 31/12/2025 | N | 31/12/2025 | 31/12/2026
81 |  | Develop and operationalize MIS for efficient forecast and planning of revenues and its mobilization strategy | Government Of Rwanda | International Competitive Bidding | 23/10/2025 | 28/10/2025 | 01/12/2025 | 30/01/2026 | 12/02/2026 | N | 12/02/2026 | 31/08/2026 | Timelines my change
82 |  | Detailed studies for construction of 8 critical ravines | Government Of Rwanda | National Competitive Bidding | 23/10/2025 | 30/10/2025 | 24/11/2025 | 17/12/2025 | 17/02/2026 | N | 17/02/2026 | 16/06/2026
83 | Consultant Services | Hiring Law firms | Government Of Rwanda | National Competitive Bidding | 25/10/2025 | 30/10/2025 | 24/11/2025 | 14/12/2025 | 14/01/2026 | N | 14/01/2026 | 13/01/2027
84 |  | Development of Kigali Street Addressing Guidelines, naming and uploading on Google Maps in selected streets | Government Of Rwanda | National Competitive Bidding | 25/10/2025 | 30/10/2025 | 24/11/2025 | 12/12/2025 | 12/01/2026 | N | 12/01/2026 | 11/09/2026
85 |  | Hiring a Transport Economist Consultant to provide technical assistance in implementing Rwanda Urban Mobility Improvement Project | Grants | International Competitive Bidding | 26/10/2025 | 31/10/2025 | 15/12/2025 | 21/01/2026 | 30/01/2026 | N | 30/01/2026 | 31/12/2026 | Timelines may change
86 |  | Hiring a consultant firm to study the Funding and financing of public transport in CoK | Grants | International Competitive Bidding | 31/10/2025 | 03/11/2025 | 03/12/2025 | 24/12/2025 | 01/01/2026 | N | 01/01/2026 | 01/01/2027 | Timelines may change
87 |  | Hiring individual consultant as a Traffic Management Expert to support Rwanda Urban Mobility Improvement Project | Grants | International Competitive Bidding | 28/10/2025 | 07/11/2025 | 31/12/2025 | 23/01/2026 | 13/02/2026 | N | 13/02/2026 | 31/12/2026
88 |  | Tender for supervision of Nyabugogo Multi Modal Transit Terminal and terminal area development (ToD) | Grants | International Competitive Bidding | 31/12/2025 | 05/01/2026 | 05/02/2026 | 27/02/2026 | 17/03/2026 | N | 17/03/2026 | 17/03/2027
89 | Consultant Services | Consultancy firm for Rwanda Urban Mobility Project/Public Transport | Grants | National Competitive Bidding | 02/02/2026 | 16/02/2026 | 16/03/2026 | 30/03/2026 | 13/04/2026 | N | 13/04/2026 | 12/03/2027
90 |  | Consultancy services for Development of technical guidelines for EV charger deployment | Grants | International Competitive Bidding | 26/02/2026 | 26/02/2026 | 15/04/2026 | 30/04/2026 | 22/05/2026 | N | 22/05/2026 | 31/12/2026 | Timelines can change
91 |  | Consultancy services for Assessment of the new electricity tariff methodology adequacy for EV charging | Grants | International Competitive Bidding | 23/02/2026 | 27/02/2026 | 15/04/2026 | 07/05/2026 | 21/05/2026 | N | 21/05/2026 | 31/12/2026 | Timelines can change
92 |  | Hiring a consultancy firm for preparation of resettlement action plans for Nyabugogo Bus Terminal and its temporary relocation sites and for the identified Dedicated Bus Lane | Grants | National Competitive Bidding | [7 empty] | 26/09/2025
93 |  | Consultancy Services to Prepare Environmental and Social Impacts Assessment (ESIA) and Resettlement Action Plans (RAPs) for three Neighborhoods in the City of Kigali. | Grants | National Competitive Bidding | [5 empty] | N |  | 06/10/2025
94 | Consultant Services | Construction Supervision Consultancy for Nyabisindu and Nyagatovu informal settlement upgrading civil works | Grants | International Competitive Bidding | [7 empty] | 15/12/2025
95 |  | Consultancy Services for the Detailed Engineering Design and works supervision for socio economic facilities (Lot 1) and public spaces (Lot 2) of Kigali Informal Settlements Upgrading Project (KISUP) | Grants | International Competitive Bidding | [7 empty] | 27/04/2028
96 |  | TA for consultancy services for storm-water management master plan in the CoK | Grants | International Competitive Bidding | [7 empty] | 29/10/2025
97 |  | Consultancy services to supervise Kigali City Infrastructure project | Government Of Rwanda | International Competitive Bidding | [7 empty] | 07/09/2026
98 |  | Consultancy services for provision of technical assistances to SPIU /KISUP team for implementing KISUP activities | Grants | International Competitive Bidding | [7 empty] | 31/12/2026
99 | Consultant Services | Feasiblity study for Development of Mont Kigali Trails Circuit (Biking & Hinking) developped | Government Of Rwanda | National Competitive Bidding | [7 empty] | 12/09/2025
100 |  | Consultancy Services for the preparation of Environmental and Social Impact Assessment and resettlement action plan Instruments and supervision (Monitoring) of their implementation | Grants | International Competitive Bidding | [7 empty] | 29/09/2028
101 |  | Recruitment of Consultancy Services for preparation of 3 neighborhood development Plans (Feasibility Studies, Detailed Designs and Tender Document) in the City of Kigali | Grants | International Competitive Bidding | [5 empty] | N |  | 08/02/2026
102 |  | Advisory services on Nature Based solutions Integration for KISUP (urban settlement upgrading project) | Grants | International Competitive Bidding | [7 empty] | 24/06/2028
103 | Consultant Services | Consultancy services to support in the establishment of a Special Purpose Vehicle tasked with the elaboration and implementation of complex urban transformation processes | Grants | Single Source | [7 empty] | 03/03/2026
104 |  | Supervision of Mageragere Memorial Genocide Memorial site Phase 2 | Government Of Rwanda | National Competitive Bidding | [7 empty] | 29/04/2026
105 |  | Consultancy services for design and supervision of a landscape plan, small workshop and 1 Block for Rental Housing Scheme in Mpazi | Grants | Single Source | [7 empty] | 23/02/2026
106 |  | Supervision shelter to needy genocide survivors | Government Of Rwanda | National Competitive Bidding | [7 empty] | 14/10/2025
107 |  | Consultancy Services to provide Contract Management and Construction Supervision for the Gatenga Informal Settlements Upgrading Works | Grants | International Competitive Bidding | [7 empty] | 14/11/2025
108 | Consultant Services | Consultancy Services for the Detailed Engineering Design and works supervision for Infrastructure of Kigali Informal Settlements Upgrading Project_(KISUP): Re-advertisement | Grants | International Competitive Bidding | [7 empty] | 28/04/2029
109 |  | Consultancy services for the development of the legal framework for housing development in Rwanda | Grants | International Competitive Bidding | [7 empty] | 30/09/2026
110 |  | Hiring 3 Law Firms (Legal Council) | Government Of Rwanda | National Competitive Bidding | [5 empty] | N |  | 25/09/2025
111 |  | Hiring an individual consultant to support Rwanda Urban Mobility Project/Transport economist | Grants | National Competitive Bidding | [5 empty] | N |  | 31/12/2025
112 |  | Consultancy Services to provide Design Review, Contract Management and Construction Supervision for the 6 Flood Risk Hotspots Rehabilitation Works | Grants | International Competitive Bidding | [7 empty] | 01/11/2025
113 | Consultant Services | Consultancy services for the feasibility study and pre-operationalization of Housing solutions and provision of technical assistance for the implementation of the solutions. | Grants | International Competitive Bidding | [7 empty] | 30/10/2026
114 |  | Consultancy services for supervision of road maintenance works in the City of Kigali | Government Of Rwanda | National Competitive Bidding | [7 empty] | 21/11/2025
115 |  | Maintenance and support of the system of CoK Masterplan monitored using Satellite imagery and changes detection | Government Of Rwanda | National Competitive Bidding | [7 empty] | 07/11/2025
116 | Non Consultant Services | Provision of Online, Radio and TV broadcasting services | Government Of Rwanda | National Competitive Bidding | 13/08/2025 | 20/08/2025 | 15/09/2025 | 07/10/2025 | 07/11/2025 | N | 07/11/2025 | 06/11/2026
117 |  | Maintenance of CCTV cameras at Nyabugogo and Nyanza Taxi parks | Government Of Rwanda | National Competitive Bidding | 22/08/2025 | 26/08/2025 | 18/09/2025 | 10/10/2025 | 10/11/2025 | N | 10/11/2025 | 09/11/2026
118 |  | Maintenance works of traffic lights and pelican crossing | Government Of Rwanda | National Competitive Bidding | 22/08/2025 | 26/08/2025 | 18/09/2025 | 08/10/2025 | 08/11/2025 | N | 08/11/2025 | 07/11/2026
119 |  | New installation of public street lights of selected roads | Government Of Rwanda | International Competitive Bidding | 22/08/2025 | 26/08/2025 | 30/09/2025 | 23/10/2025 | 23/11/2025 | N | 23/11/2025 | 22/11/2026
120 | Non Consultant Services | Supply and installation of CCTV cameras at Gatsata Exhibit Parking | Government Of Rwanda | National Competitive Bidding | 22/08/2025 | 26/08/2025 | 18/09/2025 | 10/10/2025 | 10/11/2025 | N | 10/11/2025 | 09/11/2026
121 |  | Management of Imbuga City Walk | Government Of Rwanda | National Competitive Bidding | 25/08/2025 | 29/08/2025 | 22/09/2025 | 14/10/2025 | 23/10/2025 | N | 23/10/2025 | 23/10/2026 | Timelines my change
122 |  | Rent of CoK commercial rooms/shops in Nyarugenge Sector's administrative building | Government Of Rwanda | National Competitive Bidding | 25/08/2025 | 29/08/2025 | 22/09/2025 | 13/10/2025 | 23/10/2025 | N | 23/10/2025 | 23/10/2026 | Timelines my change
123 |  | Management of Nyanza Bus Park | Government Of Rwanda | National Competitive Bidding | 25/08/2025 | 29/08/2025 | 22/09/2025 | 13/10/2025 | 23/10/2025 | N | 23/10/2025 | 23/10/2026 | Timelines my change
124 |  | Tender for irrigation of landscaping of City of Kigali Selected roads | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 10/10/2025 | 10/11/2025 | N | 10/11/2025 | 09/11/2026
125 |  | Tender for hiring company for roads waste collection | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 10/10/2025 | 10/11/2025 | N | 10/11/2025 | 09/11/2026
126 |  | Provision of insurance services for City of Kigali Assets | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 12/10/2025 | 12/11/2025 | N | 12/11/2025 | 11/11/2026
127 |  | Provision of world class audio-visual (sono, stage,…) for high level events | Government Of Rwanda | National Competitive Bidding | 25/08/2025 | 30/08/2025 | 22/09/2025 | 12/10/2025 | 12/11/2025 | N | 12/11/2025 | 11/11/2026
128 | Non Consultant Services | Provision of mobile toilets | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 12/10/2025 | 12/11/2025 | N | 12/11/2025 | 11/11/2026
129 |  | Provision of insurance services for the buildings of City of Kigali | Government Of Rwanda | National Competitive Bidding | 25/08/2025 | 30/08/2025 | 22/09/2025 | 12/10/2025 | 12/11/2025 | N | 12/11/2025 | 11/11/2026
130 |  | Tender for greening, gardening and planting trees on demand | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 10/10/2025 | 10/11/2025 | N | 10/11/2025 | 09/11/2026
131 |  | Tender for provision of hotel services for the City of Kigali | Government Of Rwanda | National Competitive Bidding | 25/08/2025 | 30/08/2025 | 24/09/2025 | 14/10/2025 | 14/11/2025 | N | 14/11/2025 | 13/11/2026
132 |  | Provision of drones and aerial coverage services | Government Of Rwanda | National Competitive Bidding | 25/08/2025 | 30/08/2025 | 26/09/2025 | 14/10/2025 | 14/11/2025 | N | 14/11/2025 | 13/11/2026
133 |  | Tender for Implementation of Kigali Street Addressing | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 10/10/2025 | 10/11/2025 | N | 10/11/2025 | 09/11/2026
134 |  | Extension of CCTV Cameras for Kicukiro District | Government Of Rwanda | National Competitive Bidding | 25/08/2025 | 30/08/2025 | 22/09/2025 | 12/10/2025 | 12/11/2025 | N | 12/11/2025 | 12/02/2026
135 |  | Supply and installation of fireworks display for vibrant Kigali | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 10/10/2025 | 10/11/2025 | N | 10/11/2025 | 01/01/2026
136 | Non Consultant Services | Acquisition of advertisement, announcement and online promotion services | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 10/10/2025 | 10/11/2025 | N | 10/11/2025 | 09/11/2026
137 |  | Provision of Sports Services to the CoK staff | Government Of Rwanda | National Competitive Bidding | 28/08/2025 | 30/08/2025 | 22/09/2025 | 14/10/2025 | 14/11/2025 | N | 14/11/2025 | 13/11/2026
138 |  | Provision of Insurance services for vehicles &Motorcycle | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 10/10/2025 | 10/11/2025 | N | 10/11/2025 | 09/11/2026
139 |  | Tender for Garden and Palm trees fumigation | Government Of Rwanda | National Competitive Bidding | 25/08/2025 | 30/08/2025 | 22/09/2025 | 12/10/2025 | 12/11/2025 | N | 12/11/2025 | 11/11/2026
140 |  | Provision of world class decoration | Government Of Rwanda | National Competitive Bidding | 23/08/2025 | 30/08/2025 | 22/09/2025 | 12/10/2025 | 12/11/2025 | N | 12/11/2025 | 11/11/2026
141 |  | Tender for trees planting and forest rehabilitiation | Government Of Rwanda | Force Account | 23/09/2025 | 26/09/2025 | 30/09/2025 | 03/10/2025 | 10/10/2025 | N | 10/10/2025 | 30/05/2026 | Timelines my change
142 |  | Upgrading City Hall conference rooms (CoK and Nyarugenge District) | Government Of Rwanda | National Competitive Bidding | 25/10/2025 | 30/10/2025 | 24/11/2025 | 12/12/2025 | 12/01/2026 | N | 12/01/2026 | 11/06/2026
143 |  | Maintenance of smart waste system | Government Of Rwanda | National Competitive Bidding | 25/11/2025 | 30/11/2025 | 22/12/2025 | 10/01/2026 | 10/02/2026 | N | 10/02/2026 | 09/02/2027
144 | Non Consultant Services | Maintenance of offices equipments | Government Of Rwanda | National Competitive Bidding | 23/11/2025 | 30/11/2025 | 22/12/2025 | 12/01/2026 | 12/02/2026 | N | 12/02/2026 | 11/02/2027
145 |  | Maintenance of City of Kigali premises | Government Of Rwanda | International Competitive Bidding | 25/12/2025 | 30/12/2025 | 03/02/2026 | 20/02/2026 | 20/03/2026 | N | 20/03/2026 | 19/03/2027
146 |  | Cleaning of the City of Kigali premises and surrounding garden | Government Of Rwanda | National Competitive Bidding | 01/04/2026 | 08/04/2026 | 30/04/2026 | 20/05/2026 | 20/06/2026 | N | 20/06/2026 | 19/06/2027
147 |  | Demolition of illegal infrastructure, including buildings, billboards, towers, and other structures that pose a threat to the general public | Government Of Rwanda | National Competitive Bidding | [7 empty] | 08/11/2025
148 |  | Maintenance works of traffic lights and pelican crossing | Government Of Rwanda | National Competitive Bidding | [7 empty] | 02/11/2025
149 |  | Maintenance of sound video system | Government Of Rwanda | National Competitive Bidding | [7 empty] | 11/12/2025
150 |  | Acquisition and Installation of Luggage scanner | Government Of Rwanda | National Competitive Bidding | [7 empty] | 23/08/2025
151 |  | Re-advertised of tender for Design and printing of promotional materials | Government Of Rwanda | National Competitive Bidding | [7 empty] | 02/08/2025
152 | Non Consultant Services | Promotional materials and service provision of sound system and audio-visual production, advertising service of the City of Kigali | Government Of Rwanda | National Competitive Bidding | [7 empty] | 07/12/2025
153 |  | Tender to install, operate and maintain street lights in selected streets in the City of Kigali through advertisement mechanism Lot 1 | Government Of Rwanda | National Competitive Bidding | [7 empty] | 14/08/2025
154 |  | Hiring company for under Veterinary Sanitary mandate for Livestock artificial insemination and vaccination against diseases for Nyarugenge District | Government Of Rwanda | National Competitive Bidding | [7 empty] | 19/03/2026
155 |  | Tender for hiring Boat | Government Of Rwanda | National Competitive Bidding | [7 empty] | 08/11/2025
156 |  | Tender for maintenance of CCTV cameras at Nyabugogo and Nyanza Taxi parks | Government Of Rwanda | National Competitive Bidding | [7 empty] | 27/09/2025
157 | Non Consultant Services | Tender for maintenance of waste water treatment plant in Gacuriro real estate and IDP model Villages | Government Of Rwanda | National Competitive Bidding | [7 empty] | 04/01/2026
158 |  | Maintenance of ICT Equipment, network infrastructure, Cooling systems | Government Of Rwanda | National Competitive Bidding | [7 empty] | 30/11/2025
159 |  | Tender for Maintenance of CoK premises | Government Of Rwanda | International Restricted Tendering | [7 empty] | 13/04/2026
160 |  | Supply and fix rain water harvesting system in schools | Government Of Rwanda | National Competitive Bidding | [7 empty] | 30/09/2025
161 |  | Provision of car tracking and installation systems | Government Of Rwanda | National Competitive Bidding | [7 empty] | 26/03/2026
162 |  | Hiring Company for Security services | Government Of Rwanda | National Competitive Bidding | [7 empty] | 21/12/2025
163 |  | Maintenance of CCTV Cameras and Security equipment | Government Of Rwanda | National Competitive Bidding | [7 empty] | 12/12/2025
164 |  | Provision of CoK Staff facilitation for sports activities | Government Of Rwanda | National Competitive Bidding | [7 empty] | 10/11/2025
165 | Non Consultant Services | Hiring court bailiff Law Firms | Government Of Rwanda | National Competitive Bidding | [7 empty] | 18/07/2026
166 |  | Provide cleaning services in peri-Urban Roads | Government Of Rwanda | National Competitive Bidding | [7 empty] | 27/03/2026
167 |  | Tender for cleaning and greening of some roads of 54Km Project | Government Of Rwanda | National Competitive Bidding | [7 empty] | 21/03/2026
168 |  | Cleaning Services of all Tarmac road (30.79 km) in Nyarugenge Sector | Government Of Rwanda | National Competitive Bidding | [7 empty] | 28/11/2025
169 |  | Provision of Insurance services for vehicles &Motorcycle | Government Of Rwanda | National Competitive Bidding | [7 empty] | 29/09/2025
170 |  | Provision of CoK Staff sports equipment | Government Of Rwanda | National Competitive Bidding | [7 empty] | 08/11/2025
171 |  | Supply and Fix Windows, Doors in classrooms | Government Of Rwanda | National Competitive Bidding | [7 empty] | 15/12/2025
172 |  | Cleaning of the City of Kigali premises and surrounding garden | Government Of Rwanda | National Competitive Bidding | [7 empty] | 07/05/2026
173 |  | Tender for provision of hotel services for the City of Kigali | Government Of Rwanda | National Competitive Bidding | [7 empty] | 27/11/2025
174 | Non Consultant Services | Tender for septic tank emptying | Government Of Rwanda | National Competitive Bidding | [7 empty] | 10/04/2026
175 |  | Tender to install, oparate and maintain street lights in selected streets in the City of Kigali through advertisement mechanism Lot 3 | Government Of Rwanda | National Competitive Bidding | [7 empty] | 14/08/2025
176 |  | Service of cleaning on the road Nyabugogo-Kimisagara-Nyakabanda-tapi rouge and stone, paved road of baoba in Nyarugenge District/ Nyarugenge | Government Of Rwanda | National Competitive Bidding | [7 empty] | 27/05/2026
177 |  | Provision of tents, chairs, table and decoration services | Government Of Rwanda | National Competitive Bidding | [7 empty] | 04/09/2025
178 |  | Provision of radio and television broadcasting services and supplements in online newspapers | Government Of Rwanda | National Competitive Bidding | [7 empty] | 24/11/2025
179 |  | Provision of insurance services for the buildings of City of Kigali and Nyamirambo Stadium | Government Of Rwanda | National Competitive Bidding | [7 empty] | 25/09/2025
180 | Non Consultant Services | Hiring company for under Veterinary Sanitary mandate for Livestock artificial insemination and vaccination against diseases for Kicukiro District | Government Of Rwanda | National Competitive Bidding | [7 empty] | 19/03/2026
181 |  | Implementation of planting specialized trees on urban roads, peri-urban roads, public gardens, forest rehabilitation and maintenance, bamboo plantation and fruits distribution in CoK FY24-25 | Government Of Rwanda | Force Account | [7 empty] | 20/04/2026
182 |  | Providing Car wash services | Government Of Rwanda | National Competitive Bidding | [7 empty] | 07/08/2026
183 |  | Tender of providing the service of cleaning for the 6.1 Kms asphalt, and stone paved roads of Gitega and Kimisagara Sector in Nyarugenge District/Nyarugenge | Government Of Rwanda | National Competitive Bidding | [7 empty] | 13/09/2025
184 | Non Consultant Services | Hiring company for under Veterinary Sanitary mandate for Livestock artificial insemination and vaccination against diseases for Gasabo District | Government Of Rwanda | National Competitive Bidding | [7 empty] | 19/03/2026
185 |  | Providing the service of cleaning services for the 6.302Km asphalt and stone paved roads of Rwezamenyo Sector in Nyarugenge District | Government Of Rwanda | National Competitive Bidding | [7 empty] | 06/09/2025
186 |  | Provision of mobile toilets | Government Of Rwanda | National Competitive Bidding | [7 empty] | 17/10/2025
187 |  | Codification and inventory of City of Kigali | Government Of Rwanda | National Competitive Bidding | [7 empty] | 13/02/2026
188 |  | Providing the service of cleaning services in Special Economic zone | Government Of Rwanda | National Competitive Bidding | [7 empty] | 17/09/2025
189 |  | Cleaning services on the road from Chez Venant-Kuryanyuma and the stoned pavement road of Mumena /Nyarugenge+1.03 Km 1930 to Nyabugogo | Government Of Rwanda | National Competitive Bidding | [7 empty] | 28/08/2025
190 | Non Consultant Services | Repairing and maintenance of City of Kigali's vehicles and maintenance of generator | Government Of Rwanda | National Competitive Bidding | [7 empty] | 08/11/2025